## Sheet1
GULU CITY PROCUREMENT PLAN FOR WORKS,CONSULTANCY,NON CONCULTANCY AND SUPLLIES FOR SUBMISSION TO TREASURY,PPDA AND PUBLICATION:FY 2025-2026
S/No | Subject of procurement | Estimated Cost (000) UGX | Source of funding | Procurement Method | Contract Type | Procurement Type | Reservation Scheme applied? (Y/N) | Preference Scheme applied? (Y/N) | Bid Invitation Date | Bid Closing/ Opening Date | Approval Evaluation Report Date | Award Notification Date | Contract signing date (Estimate Date) | Completion Date (Estimate Date)
1 | Supply of motor grader | 1265500 | GOU | Open Domestic Bidding | Lumpsum contract | Supplies | No | Yes | 2025-11-07 | 2025-12-02 | 2025-12-12 | 2025-12-15 | 2026-01-20 | 2026-04-30 | GOU
2 | Maintenance of solar street lights/supplies of material | 300000 | GOU | Open Domestic Bidding | Framework contracts | Supplies | No | Yes | 2025-11-07 | 2025-12-04 | 2025-12-12 | 2025-12-15 | 2026-01-20 | 2026-06-30
3 | Constructions of Classrooms at Koro Primary School | 132000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
4 | Constructions of Classrooms at Gulu Town Primary School | 132000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
5 | Completion of Construction of Council hall at Laroo Pece City Division Office | 83664 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
6 | Construction of a chain link fence and gateman house at Alokolum Health Centre II | 63000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
7 | Construction of a chain link fence and gateman house at Lapeta Health Centre II | 58000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
8 | Construction of a chain link fence and gateman house at Unyama Health Centre II | 76000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
9 | Construction of a chain link fence and gateman house at Oitino Health Centre II | 108000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
10 | Renovation of premises in Bardege Layibi Division | 40500 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
11 | Renovation of Laroo Primary School | 40000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
12 | Renovation of Layibi Primary School | 40000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
13 | Renovation of Gulu Core PTC | 42000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
14 | Renovation of one block with three classrooms and office at Laroo Adra Primary school | 40000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
15 | Renovation of an office block at Layibi Central Primary school | 10000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
16 | Renovation of staff quarters at Unyama HC II | 30000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-24 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
17 | Renovation of staff quarters at Alokolum HC II | 18646 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
18 | Renovation of Public Library in Bardege Layibi Division | 50000 | GOU | Quotation method | Admeasurement | Works | No | No | 2025-10-15 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
19 | Supply of Assorted road materials and hard ware materials Double cabin Pickup for Finance department | 141464 | GOU | Quotation method | Lumpsum | Supplies | No | Yes | 2025-10-15 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
20 | Supply of Double cabin Pickup for Finance department | 141464 | GOU | Quotation method | Lumpsum | Supplies | No | Yes | 2025-10-15 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
21 | Supply of Double cabin Pickup for Laroo Pece Division | 175312 | GOU | Quotation method | Lumpsum | Supplies | No | Yes | 2025-10-15 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
22 | Supply of Land at Laroo HC II | 20000 | GOU | Direct Procurement | Lumpsum | Supplies | No | No | 2025-10-15 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2025-12-01
23 | Supply of Public adress system for Laroo Pece Division | 30000 | GOU | Quotation method | Lumpsum | Supplies | No | No | 2025-10-15 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
24 | Supply and installation of a Solar System to Laroo Pece Division | 30000 | GOU | Quotation method | Lumpsum | Supplies | No | No | 2025-10-15 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2026-03-30
25 | Procurement of assorted office and school Furniture | 80000 | GOU | Open Domestic Bidding | Framework contracts | Supplies | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
26 | Supply of Furniture at St.Kizito Aywee | 16000 | GOU | Open Domestic Bidding | Framework contracts | Supplies | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
27 | Supply of fuel and lubricants | 360000 | GOU | Open Domestic Bidding | Framework contracts | Supplies | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
28 | Supply of stationery and office consumeables | 190000 | GOU | Open Domestic Bidding | Framework contracts | Supplies | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
29 | Supply of Printed materials | 10000 | GOU | Open Domestic Bidding | Framework contracts | Supplies | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
30 | Supply of Computers , printers , binding machines /ICT/office Equipment | 72000 | GOU | Open Domestic Bidding | Framework contracts | Supplies | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
31 | Supply of agricultural inputs, assorted trees/ Seedling | 13000 | GOU | Open Domestic Bidding | Framework contracts | Supplies | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
32 | Provision of Hotel services ( Meals , refreshments, conference facilities etc) | 122000 | GOU | Open Domestic Bidding | Framework contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
33 | Provision of Electricity | 14000 | GOU | Direct Procurement | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
34 | Repair & maintenance of motor vehicles , motorcycles and road equipment | 70000 | GOU | Open Domestic Bidding | Framework contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
35 | Sevicing & maintenance of office equipments | 30000 | GOU | Open Domestic Bidding | Framework contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
36 | Sevicing & maintenance of fire fighting equioment | 15000 | GOU | Open Domestic Bidding | Framework contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
37 | Provision of Consultancy Services-Legal | 200000 | GOU | Open Domestic Bidding | Framework contract | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
38 | Provision of Security Guard services | 32910 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
39 | Provision of Advertisement services | 10000 | GOU | Direct Procurement | Lumpsum contracts | Non-Consultancy Services | No | No | 6/31/2025 | 0 | 0 | 0 | 2025-07-01 | 2025-07-03 | GOU
40 | Collection of revenue from Gulu main market public toilet Group B (LOT 2,3,8,11,12) laroo pece city division | 3200 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
41 | Collection of revenue from Gulu main market public toilet Group C (LOT 4,6,7,13,15) Laroo pece city division | 8500 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
42 | Collection of revenue from Gulu main market public toilet Group A (LOT 1,5,9,10,14) | 7100 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
43 | Rental of former administration office at Gulu main bus park | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
44 | Rental of former enforcement block at Gulu main bus park | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
45 | Renting of big eating house in Gulu main bus park | 4500 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
46 | Collection of revenue from animals slaughter fees from Unyama site. in laroo pece division | 15000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
47 | Collection of revenue from animals slaughter fees from Twon Okun site. in Laroo pece City division | 12000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
48 | Collection of market due from layibi central market | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
49 | Collection of revenue from market dues wilobo market | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
50 | Collection of market due from laliya market in Laroo Pece Division | 5000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
51 | Collection of market due from Unyama market in Laroo-Pece Division | 4200 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
52 | Collection of revenue from pig Slaughter fees in pece laroo Division. | 6200 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
53 | Collection of revenue from bus park public toilet Laroo pece division | 23520 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
54 | Collection of animal slaughter fees at Gulu main Abbatoir in Bardege Layibi DivisionS | 60000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
55 | Collection of Revenue from TUK TUK operators in Bardege Layibi DivisionS | 8200 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
56 | collection of revenue from vehicle loading and offloading at customs corner stage in Bardege Layibi Division | 2700 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
57 | Collection of revenue from trucks and lorry park fee from Kaunda grounds in Berdega Layibi Division | 3600 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
58 | Collection from Johnson Wilobo and Mak Paco markets in Bardege Layibi Division | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
59 | Collection of toilet entry fees for two public toilets at Kaunda grounds in Bardege Layibi Division | 4100 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
60 | Colllection of market dues and gate charges from olayo-ilong Mrket in Brdege Layibi Division | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
61 | Collection of animal slaughter fee from fresh pork in Bar dege Layibi Division | 6500 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | Yes | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
62 | Colllection of market dues and gate charges from olayo-ilong Mrket in Brdege Layibi Division | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
63 | collection of markert dues and gate charges from Layibi lacor market in bardege layibi division | 3000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
64 | Collection of market dues and gate charges from kabedopong market | 3000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
65 | Collection of revenue from hotel taxes in Bardege- layibi division | 19000 | GOU | Open Domestic Bidding | Framework contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
66 | Collection of revenue from hotel taxes in Laroo- Pece division | 3600 | GOU | Open Domestic Bidding | Framework contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
67 | Collection of revenue from Gulu main bus Park in Laroo pece division | 4000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
68 | Collection of revenue from advertising tools(including post) and LED screens in Gulu city | 34000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
69 | Renting former Health Unit Bus park Laroo Pece Division | 7000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
70 | Collection of revenue from street parking,produce and off loading fees Laroo pece city division | 20 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
71 | Collection of revenue from bus park public toilet in Laroo Pece Division | 23520 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
72 | Renting of big eating house in Gulu main bus park | 4500 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
73 | Collection of Hotel Tax on commission in Laroo Pece City Division | 150000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
74 | Collection of Evening Market Due infront of Gulu main market in pece laroo city Division. | 8000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
75 | Collection of revenue from pig Slaughter fees in pece laroo Division. | 6200 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
76 | Collection of revenue from animals slaughter fees from Twon Okun In Laroo Pece Division | 12000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
77 | Collection of market due from Unyama market in Laroo-Pece division | 4200 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
78 | Collection of revenue from animals slaughter fees from Unyama in Laroo Pece division | 15000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
79 | collection of revenue from vehicle loading in front of Gulu main market | 7000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
80 | Collection of revenue from market dues wilobo market | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
81 | Collection of market due from laliya market in laroo pece city division | 5000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
82 | Collection of market due from layibi central market | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
83 | Collection of revenue from chicken roasting along Cemetery Road Evening hours | 7000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
84 | Collection of toilet entry fees for two public toilets at Kaunda grounds | 4100 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
85 | Collection of animal slaughter fee from fresh pork in Bardege Layibi Division | 6500 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | Yes | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
86 | Collection of revenue from chicken and Matooke sellers in bardege layibi Division | 3200 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
87 | Collection of market dues and gate charges from kabedopong market | 3000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | Yes | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
88 | Collection of animal slaughter fees at Gulu main Abbatoir in Bardege Layibi Division | 60000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
89 | Collection of Revenue from TUK TUK operators in Bardege Layibi Divisions | 8200 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
90 | Collection of revenue from dealers in street parking, loading and off loading in bardege-layibi Division | 182100 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
91 | collection of revenue from vehicle loading and offloading at customs corner stage in Bardege Layibi Division | 2700 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
92 | Collection from Johnson Wilobo and Mak Paco markets | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
93 | Colllection of market dues and gate charges from olayo-ilong Market | 2000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
94 | collection of markert dues and gate charges from Layibi lacor market | 3000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
95 | Collection of revenue from trucks and lorry park fee from Kaunda grounds | 3600 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
96 | Collection of revenue from trucks and lorry park along Odur Min Odyek road | 2900 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
97 | Collection of Toilet entry fees from Lacor Complex Market | 1500 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
98 | Enforcement of Collection of revenue from sign posts and bilboards in Gulu City | 40000 | GOU | Open Domestic Bidding | Lumpsum contracts | Non-Consultancy Services | No | No | 2025-04-06 | 6/27/2025 | 2025-10-07 | 2025-11-07 | 7/29/2025 | 6/30/2026
|  | Name: |  |  | Approved by: |  | Name:
|  | Signature: |  |  |  |  | Signature:
|  | Designation: | Head PDU |  |  |  | Designation:
|  | Date: |  |  |  |  | Date:

## Sheet4
| 12 | 3100000000 | 37200000000
| 10 | 4000000 | 40000000
| 10 | 3100000000 | 31000000000
| 10 | 2352000 | 23520000
| 10 | 1500000 | 15000000
| 10 | 710000 | 7100000
| 10 | 15000000 | 150000000
5000000 | 9 | 45000000 | 12
540000000